## Sheet1
Risk | Risk Statement | Response Strategy | Objectives | Likelihood | Impact | Risk Level
Illness | The rate of completing the project will be negatively impacted due to illness | Rest and create a project plan that can account for the time loss due to illness | To protect your health and recover as well as reduce the impact of time lost | Medium | High | 8
Internet Failure | The rate of completing the project will be negatively impacted due to illness | Contact network provider and/or use your phone to connect to the internet for short-term internet access. | To ensure the completion of the project objectives on time by reducing the impact of losing internet connectivity. | Low | Medium | 4
Technical Difficulties | mistakenly erasing your entire project, or sections of my project from your computer. | Ensure all files are routinely pushed on GitHub so that data may be cloned from the repository in the event of a loss. | To ensure access to the website throughout development and post deployment. | Low | High | 7
Loss/Broken of laptop | A broken laptop would result in not being able to complete the project | Have another device that is accessible to you, that allows the download all of the necessary software for this project and use GitHub to clone your recent progress | To ensure access to yuour work regardless of which device. | Low | High | 7
GitHub Failure | GitHub servers going down leads to temporarily not having access to your repository or to losing data and development progress | Make a regular hard backup on a non-cloud service | To ensure you don't loose your work | Low | High | 7
Failure to Meet Project Deadline | Poor time management leading to the product not being deployed by the deadline | Ensure project is planned thoroughly and managed throughout. | Finish project on time and to a good standard. | Low | High | 7
Hardware Failure | Renewals aren't carried out for web server and domain names leading to website outages until contracts are renewed. | Ensure that all contracts are available to be viewed by relevant parties, and calendar entries are set up with remonders, while also setting up email notifications for when renewals are due. | Prevent the domain name from being lost and having outages due to the web server being removed as it is no longer in service. | Low | High | 7
Joint Pains | Constantly sitting could lead to a negative impact on the physical body | It is important to stand and stretch every hour to prevent joint pains | To protect your health and ensure you're not damaging your physical body | High | Medium | 6
Impact
[9 empty] | Low | Medium | High
[7 empty] | Liklihood | Low | 1 | 4 | 7
[8 empty] | Medium | 2 | 5 | 8
[8 empty] | High | 3 | 6 | 9